## Summary
CHARTER HOUSE – AI AGENT MVP BUILD ¦ ESTIMATION SUMMARY
Variables |  |  |  | Team Allocation |  |  |  | S.N. ¦ Pre-Requisites (Client Responsibility)
SNO | Variables | # |  | SNO | Role | Allocation % | Est. Days | 1 | Active Azure subscription with Contributor or Owner role on the target subscription.
1 | Front End | No |  | 1 | Project Manager | 33% | 17.3203 | 2 | Microsoft 365 E3 (or higher) licenses for all service and user accounts.
2 | Backend (AI Agent Dev) | Yes |  | 2 | AI Architect / Lead | 50% | 26.2429 | 3 | Copilot Studio license (standalone ~$200/tenant/mo or via M365 Copilot SKU).
3 | DevOps & Cloud | Yes |  | 3 | AI Engineer | 100% | 52.4857 | 4 | Read-access SharePoint credentials and Graph API permissions for ECI team.
|  |  |  | 4 | QA Engineer | 50% | 26.2429 | 5 | Microsoft Teams admin consent for custom Copilot Studio bot deployment.
Activities |  |  |  | 5 | DevOps / Cloud Eng | 25% | 13.1214 | 6 | Azure AD user accounts provisioned UAT users prior to UAT phase.
SNO | Activities |  | DevTime (hrs)
1 | Front End |  | 0
2 | AI Agent Dev |  | 310.75 | Monthly Infra Cost (Est.) |  | 581.65
3 | DevOps & Cloud |  | 56.65 |  |  |  |  | S.N. ¦ Out of Scope
[8 empty] | 1 | Automated / scheduled data ingestion pipelines from any source.
| Component | Days | Weeks |  |  |  |  | 2 | Data ingestion from sources outside SharePoint, PDF, or Word.
| Front End | 0 | 0 |  |  |  |  | 3 | Custom UI development for Teams, web, or mobile platforms.
| AI Agent Dev | 44.3929 | 8.8786 |  |  |  |  | 4 | Building CI/CD pipelines or advanced deployment automation.
| DevOps & Cloud | 8.0929 | 1.6186 |  |  |  |  | 5 | PPT, Excel, image, audio, or video file types as agent inputs.
| Project Duration without UAT |  | 8.8786 |  |  |  |  | 6 | Long-term AI operations support or enterprise-wide AI platform.
| UAT | 10 | 2 |  |  |  |  | 7 | Unstructured formats (scanned images, audio, video) as data sources.
| Project Duration with UAT |  | 10.8786 |  |  |  |  | 8 | Data classification, sensitivity labelling, or DLP integration.
| Project Duration incl. Leaves & Holiday | [6 empty] | 9 | Any of the 9 remaining Charter House use cases not in MVP scope.
| Leaves & Holiday | 1 | Weeks |  |  |  |  | 10 | Multi-language support for NDA review or DDQ drafting.
| Weeks |  | 11.8786 |  |  |  |  | 11 | DocuSign integration or automated email dispatch of outputs.
Note: With 2 AI Engineers running NDA + DDQ build in parallel, project can be completed within 5-6 weeks | [7 empty] | 12 | LP-specific personalisation engine (Phase 2 roadmap item).
[8 empty] | 13 | Any features not explicitly listed in scope (subject to change request).
S.N. ¦ Assumptions
[8 empty] | 1 | Source files are PDF and Word only , all other formats excluded from MVP scope.
[8 empty] | 2 | 50-100 historical files per use case (NDAs + DDQs) provided within Week 1.
[8 empty] | 3 | AI accuracy estimated at 80–95% for structured document comparison tasks.
[8 empty] | 4 | AI responses are advisory - all outputs require human review before use.
[8 empty] | 5 | Model accuracy depends on quality, consistency, and volume of source files provided.
[8 empty] | 8 | Charter House standard NDA template provided in editable Word format (baseline for comparison).
[8 empty] | 9 | One-time ingestion only , no automated real-time or scheduled data sync in MVP.
[8 empty] | 10 | UAT phase follows agreed timeline; client resources available and committed.
[8 empty] | 11 | Data classification and labelling not required for the POC phase.
[8 empty] | 12 | 10–15 users participate in UAT, each running ~50–100 queries per agent.
[8 empty] | 13 | All UAT users have existing SharePoint / file access to source documents.
[8 empty] | 14 | Prompt logs stored in Azure Monitor / Log Analytics with 30-day default retention.
[8 empty] | 15 | Client is responsible for all Azure/cloud licensing, infrastructure, and data usage costs.
[8 empty] | 16 | Client will respond to ECI queries within 24–48 business hours.
S.N. ¦ Risks
[8 empty] | 1 | AI accuracy below KPI threshold - NDA clause comparison or DDQ answer quality insufficient. Mitigation: multi-model testing; human review always included.
[8 empty] | 2 | Historical files insufficient quality or quantity (<50 files). minimum viable dataset defined upfront.
[8 empty] | 5 | Copilot Studio Teams channel blocked by client IT/AAD restrictions. Mitigation: IT admin identified in Week 1.
[8 empty] | 7 | SharePoint API permissions or access issues delay data access. Mitigation: pre-req checklist sent in Week 1; 24-48hr SLA on client responses.
[8 empty] | 8 | Word track-changes output incompatible with Charter House Word version.
[8 empty] | 12 | NDA clause variation too broad for standard comparison logic. Mitigation: clause library reviewed and categorised in Discovery phase.
S.N. ¦ Definition of Done – Project Closure Criteria
► DISCOVERY & DESIGN
[8 empty] | 1 | Architecture document reviewed and signed off by client.
[8 empty] | 2 | KPI metrics and accuracy thresholds defined, documented, and agreed by client.
[8 empty] | 3 | NDA + DDQ source files confirmed as PDF/Word; volume confirmed ≥50 files per use case.
[8 empty] | 4 | Prompt templates provided and approved for both agents. Model selection justified.
► ENVIRONMENT SETUP
[8 empty] | 1 | All Azure resources provisioned in dedicated Resource Group; private endpoints verified.
[8 empty] | 2 | Entra ID Managed Identities configured - no hardcoded secrets; Key Vault policies set.
[8 empty] | 3 | Copilot Studio bot deployed to Charter House Teams tenant with test message confirmed.
► NDA REVIEWER AGENT
[8 empty] | 1 | Document parser correctly extracts clauses from ≥95% of test NDA files.
[8 empty] | 2 | One-time ingestion complete - 50-100 NDAs indexed in AI Search with metadata.
[8 empty] | 3 | Clause comparison correctly identifies non-standard clauses in ≥80% of test cases.
[8 empty] | 4 | Word output with track changes generated; issues summary page included in all outputs.
[8 empty] | 5 | Agent accessible via Teams; NDA reviewed and output returned within 60 seconds.
► LP QUESTIONNAIRE ENGINE
[8 empty] | 1 | DDQ parser extracts all questions from ≥95% of test DDQ files (PDF and Word).
[8 empty] | 2 | One-time ingestion complete — 50-100 historical DDQ responses indexed in AI Search.
[8 empty] | 3 | RAG retrieval returns relevant answers for ≥85% of test questions (similarity ≥70%).
[8 empty] | 4 | Low-confidence answers (<70%) correctly flagged for human review in output document.
[8 empty] | 5 | Source traceability: answer tagged to source DDQ + question reference.
► TESTING & UAT
[8 empty] | 1 | All unit and integration tests passing - minimum critical open defects at UAT closure.
[8 empty] | 2 | 10-15 Charter House users completed UAT (50-100 queries each) across both agents.
[8 empty] | 3 | KPI validation report produced - accuracy vs threshold documented for both models.
[8 empty] | 4 | UAT written sign-off received from named client approver for each agent.
► PRODUCTION DEPLOYMENT & HANDOVER
[8 empty] | 2 | Technical documentation and user guides finalised and delivered to client.
[8 empty] | 4 | Admin + end-user training sessions completed; recordings provided.

## AI Agent Dev
CHARTER HOUSE – AI AGENT DEVELOPMENT & INTEGRATION (NDA Reviewer + LP Questionnaire Engine)
# | Task / Phase | Sub-task | Dev Low (hrs) | Dev High (hrs) | Avg (hrs) | Comments
Phase 1: Discovery & Design |  |  | 56 | 78 | 67
1 |  | Kickoff workshop – scope confirmation & stakeholder alignment | 8 | 10 | 9 | Joint session with Charter House Legal & IR SMEs
2 |  | Data assessment – source NDA files & DDQ response library review | 8 | 12 | 10 | Validate PDF/Word quality, structure, volume (50-100 files each)
3 |  | Architecture finalisation – AI Foundry, AI Search, App Service, Key Vault, Entra ID | 8 | 12 | 10
4 |  | NDA orchestration logic design – clause extraction, comparison & redline framework | 8 | 12 | 10 | System prompt, tool definitions, output format design
5 |  | DDQ orchestration logic design – RAG architecture (reuse ELLA logic) | 6 | 8 | 7 | Leverage existing ELLA DDQ agent; document adaptation required
6 |  | Evaluation framework – KPI metrics, accuracy thresholds, model selection (2 LLM x 2 embedding) | 6 | 8 | 7
7 |  | Technical documentation v1 – architecture, comms plan, solution design doc | 12 | 16 | 14 | ECI best practice format; client sign-off required
Phase 2A: NDA Reviewer & Standard Mark-Up Agent |  |  | 71 | 96 | 83.5
1 |  | Document parser – PDF/Word ingestion, clause boundary detection | 12 | 16 | 14
2 |  | One-time ingestion – 50-100 historical NDA files → AI Search index | 8 | 12 | 10 | Chunking strategy, metadata tagging, embedding generation
3 |  | Clause comparison engine – incoming clause vs Charter House standard position | 16 | 20 | 18 | Prompt engineering; few-shot examples for each clause type
4 |  | Redline generation – Word track-changes output via python-docx | 12 | 16 | 14 | Track changes applied to original NDA; format preservation
5 |  | Issues summary page – plain English summary of all flagged clauses | 6 | 8 | 7 | Structured output appended to Word document
6 |  | Foundry Agent Service wiring – tools, system prompt, conversation flow | 8 | 12 | 10 | Tool registration, agent orchestration logic
7 |  | Copilot Studio / Teams UI – file upload trigger, response cards | 6 | 8 | 7 | Adaptive card output; file return to Teams user
8 |  | Prompt logging – all interactions → Log Analytics (audit trail) | 3 | 4 | 3.5 | Per-query logging; source traceability
Phase 2B: LP Questionnaire Answer Engine (DDQ Agent) |  |  | 45 | 69 | 57 | ELLA DDQ agent reused — reduced hours vs NDA agent build
1 |  | DDQ parser - question extraction from PDF/Word uploads | 8 | 12 | 10 | Question boundary detection, category tagging , reuse ELLA parsing logic
2 |  | One-time ingestion - 50-100 historical DDQ responses -> AI Search index | 5 | 8 | 6.5
3 |  | RAG retrieval - semantic search against historical answers (top-k) | 8 | 12 | 10 | Similarity scoring, source tagging, confidence threshold
4 |  | Answer rewriter - Charter House house-style enforcement | 8 | 12 | 10 | Few-shot prompting; tone & style alignment - Charter House style
6 |  | Draft package output - Q&A review document with source traceability | 4 | 6 | 5 | Word output; each answer tagged to source DDQ + question ref
7 |  | Foundry Agent Service wiring - tools, system prompt, multi-step flow | 6 | 10 | 8 | Tool registration, orchestration logic
8 |  | Copilot Studio / Teams UI - file upload, Q&A display, review flow | 4 | 6 | 5 | Teams interface for IR team
9 |  | Prompt logging - all interactions → Log Analytics | 2 | 3 | 2.5 | Source traceability log for compliance
Phase 3: Testing & UAT |  |  | 42 | 60 | 51
1 |  | Internal QA – end-to-end testing both agents; test case execution | 12 | 16 | 14 | All acceptance criteria tested; defect log maintained
2 |  | KPI validation – accuracy testing | 8 | 12 | 10 | Model comparison report; threshold validation
3 |  | UAT facilitation – 10-15 Charter House users, ~50-100 queries each | 8 | 10 | 9 | Session management, issue logging, user feedback collection
4 |  | Bug fixes & prompt tuning post-UAT | 10 | 16 | 13 | Based on UAT feedback; P1/P2 issues resolved before sign-off
5 |  | Azure Monitor alerts & workflow notification testing | 4 | 6 | 5
Phase 4: Handover & Knowledge Transfer |  |  | 20 | 28 | 24
1 |  | Technical documentation – architecture diagrams, API specs | 8 | 12 | 10 | ECI standard format; delivered to client operational team
2 |  | Functional documentation – end-user guide for Teams interface | 6 | 8 | 7 | Per-agent user guide; uploaded to client SharePoint
5 |  | Knowledge transfer – 1x admin session + 1x end-user training session | 6 | 8 | 7 | 1hr each; recorded for future reference
Meetings & Sync (10% of dev hours) |  |  | 23.4 | 33.1 | 28.25 | Standups, client syncs, reviews
TOTAL AI AGENT DEV HOURS |  |  | 257.4 | 364.1 | 310.75

## Architecture
NDA Reviewer Agent
Legal & HR Team · Upload NDA (PDF/Word) via Teams → AI compares each clause against Charter House standard positions → Word output with track changes + issues summary page
LP Questionnaire Engine (DDQ Agent)
Investor Relations · Upload DDQ (PDF/Word) via Teams → RAG retrieves best historical answers → AI rewrites in Charter House house style → draft Q&A doc with source traceability

## DevOps & Cloud
CHARTER HOUSE – DEVOPS & INFRASTRUCTURE PROVISIONING
# | Task / Phase | Sub-task | Dev Low (hrs) | Dev High (hrs) | Avg (hrs) | Comments
Azure Environment Setup |  |  | 28 | 42 | 35
1 |  | Azure Resource Group | 2 | 3 | 2.5 | Isolated network foundation; naming convention per ECI standard
2 |  | Private endpoints & Private Link config (all services off public internet) | 8 | 12 | 10 | AI Foundry, AI Search, App Service, Key Vault, Storage
3 |  | Azure AI Foundry hub + project – llm model deployments | 4 | 6 | 5 | Model deployment; quota increase request in Week 1
4 |  | Azure AI Search (S1) provisioning & index schema setup | 3 | 4 | 3.5 | Two indexes: nda-clauses-index, ddq-answers-index
5 |  | Azure App Service (B2/P1v3 Linux) – backend API hosting | 2 | 3 | 2.5 | REST API + MCP Server; auto-scale config
6 |  | Azure Key Vault – secrets config, Managed Identity RBAC | 2 | 4 | 3 | No hardcoded secrets; Managed Identity for all service-to-service
7 |  | Azure Blob Storage – containers for source files & outputs | 2 | 3 | 2.5 | Hot tier LRS; lifecycle policy for staging cleanup
8 |  | Azure Monitor + Log Analytics workspace (30-day default retention) | 2 | 3 | 2.5 | Prompt log ingestion; dashboard setup
9 |  | Microsoft Entra ID – Managed Identities, app registrations | 3 | 4 | 3.5 | Service-to-service auth; Teams bot app registration
Copilot Studio & Teams Integration |  |  | 7 | 11 | 9
11 |  | Copilot Studio environment provisioning + Teams bot channel config | 4 | 6 | 5 | Bot channel setup; Teams admin consent required from client IT
12 |  | Teams admin consent + bot deployment to Charter House tenant | 3 | 5 | 4 | Admin approval gating; fallback to web UI if Teams blocked
Security Baseline & Testing |  |  | 6 | 9 | 7.5
13 |  | NSG rules, Entra Conditional Access, Key Vault access policies | 4 | 6 | 5 | Security hardening; all services private endpoint verified
14 |  | UAT staging environment deployment + smoke test | 2 | 3 | 2.5 | Mirror of production; used for UAT phase
Meetings & Sync (10% of dev hours) |  |  | 4.1 | 6.2 | 5.15 | Standups, client syncs
TOTAL DEVOPS HOURS |  |  | 45.1 | 68.2 | 56.65 | Average for budgeting

## Infra Cost
CHARTER HOUSE – AZURE INFRASTRUCTURE COST ESTIMATE ¦ Live Pricing – March 2026 ¦ Pay-As-You-Go
# | Service / Resource | $/mo | Pricing Model | Notes / Assumptions
AI Services — Azure AI Foundry / OpenAI
1 | Azure OpenAI GPT-4o (Global PAYG) - Primary LLM | 35 | Pay-per-token | Est. ~1.5M input + 0.5M output tokens/mo @ POC. $2.50/$10 per 1M. Source: azure.microsoft.com/pricing
2 | Azure OpenAI GPT-4o-mini - Model comparison / fallback | 5 | Pay-per-token | ~10% of queries. $0.15/$0.60 per 1M tokens. Used for model benchmarking in Phase 4.
3 | text-embedding-3-small - One-time ingestion (100-200 files) | 1 | Pay-per-token | ~5M tokens total one-time ingestion. $0.022/1M tokens. Negligible ongoing cost.
Subtotal — AI Services |  | 41
Vector Storage — Azure AI Search
4 | Azure AI Search - Standard S1 (1 replica, 1 partition) | 250 | Fixed monthly | S1 required for semantic ranker + hybrid search. Supports both NDA clause index + DDQ answer index. Source: azure.microsoft.com/pricing/details/search
Subtotal — Vector Storage |  | 250
Compute — App Service & Functions
5 | Azure App Service - B2 (2 vCPU, 3.5GB) Linux | 75 | Fixed monthly | Hosts FastAPI backend / REST API. B2 sufficient for POC load. ~$75/mo. Upgrade to P1v3 at production.
6 | Azure Functions - Consumption Plan | 2 | Pay-per-execution | ~500K executions/mo. First 1M free, then $0.20/1M. Near-zero cost for POC traffic levels.
7 | Azure Blob Storage - Hot LRS (~20 GB staging) | 1 | Pay-per-GB | $0.018/GB/mo. Source file staging + output documents. Lifecycle policy cleans temp files.
Subtotal — Compute |  | 78
Security & Identity
8 | Azure Key Vault - Standard tier (~50K operations/mo) | 0.15 | Operations-based | $0.03/10K ops. Holds API keys, connection strings. Managed Identity eliminates secret exposure.
9 | Microsoft Entra ID - Managed Identity & app registrations | 0 | Included in M365 E3 | No additional cost. Covered by client M365 E3 license. Managed Identity for all service auth.
Subtotal — Security & Identity |  | 0.15
Monitoring & Observability
10 | Azure Log Analytics - prompt logging (~5 GB/mo ingested) | 11.5 | Per GB ingested | $2.30/GB after 5 GB free tier. 30-day default retention. All agent interactions logged here.
11 | Azure Monitor - alert rules & dashboards | 1 | Per alert rule | 10 alert rules. First 10 rules free. Workflow failure notifications; performance monitoring.
Subtotal — Monitoring |  | 12.5
Integration — Copilot Studio & Teams
12 | Microsoft Copilot Studio - Teams bot (both agents) | 200 | Per tenant/month | ~$200/tenant/mo standalone OR included in M365 E5/Copilot SKU. Confirm client license tier.
Subtotal — Integration |  | 200
TOTAL ESTIMATED MONTHLY INFRASTRUCTURE COST (POC) |  | 581.65 |  | POC phase (10-week build, 10-15 users). Excludes one-time setup costs.

## Version History
CHARTER HOUSE – ESTIMATION VERSION HISTORY
Version | Changes / Notes | Date | Author
v1.1 |  | 2026-03-19 | Prabhakar Gupta